## Soft crawler
Create professional Gantt charts in GanttPRO in a few clicks
Soft crawler | [10 empty] | 2024-12-07 08:04
Color | WBS Number |  | Task name / Title | Assigned to | Planned start date | Planned end date | Deadline | Progress (%) | Duration (hours) | Estimated hours | Time log (minutes) | Status | Priority | Task description | Predecessor | Budget | Actual cost | Created | Creator | Type | Project | Level
| 1 | Project planning |  |  | 2024-11-13 09:00 | 2024-11-28 18:00 |  | 0 | 128 | 0 | 0 |  |  |  |  | 0 | 0 | 2024-12-04 22:57 | Fadhel Haji | project | Soft crawler | 1
| 1.1 |  | Identify team members |  | 2024-11-13 09:00 | 2024-11-13 18:00 |  | 0 | 8 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2024-12-04 22:57 | Fadhel Haji | task | Soft crawler / Project planning | 2
| 1.2 |  | Define project objectives |  | 2024-11-13 09:00 | 2024-11-13 18:00 |  | 0 | 8 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2024-12-04 23:30 | Fadhel Haji | task | Soft crawler / Project planning | 2
| 1.3 |  | Establish project timeline |  | 2024-11-13 09:00 | 2024-11-13 18:00 |  | 0 | 8 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2024-12-04 23:30 | Fadhel Haji | task | Soft crawler / Project planning | 2
| 1.4 |  | Set the project's budget |  | 2024-11-13 09:00 | 2024-11-28 18:00 |  | 0 | 128 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2024-12-04 23:30 | Fadhel Haji | task | Soft crawler / Project planning | 2
| 2 | Research and Development |  |  | 2024-11-20 09:00 | 2025-02-23 18:00 |  | 0 | 768 | 0 | 0 |  |  |  |  | 0 | 0 | 2024-12-04 23:01 | Fadhel Haji | project | Soft crawler | 1
| 2.1 |  | Conduct a literature review |  | 2024-11-20 09:00 | 2025-02-23 18:00 |  | 0 | 768 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2024-12-04 23:02 | Fadhel Haji | task | Soft crawler / Research and Development | 2
| 2.2 |  | Analyze existing pipeline technologies |  | 2024-11-27 09:00 | 2024-12-17 18:00 |  | 0 | 168 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2024-12-04 23:03 | Fadhel Haji | task | Soft crawler / Research and Development | 2
| 2.3 |  | Identify necessary materials and components (cameras, sensors) |  | 2024-12-26 09:00 | 2024-12-28 18:00 |  | 0 | 24 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2024-12-04 23:04 | Fadhel Haji | task | Soft crawler / Research and Development | 2
| 3 | Design Phase |  |  | 2025-01-05 09:00 | 2025-01-12 18:00 |  | 0 | 64 | 0 | 0 |  |  |  |  | 0 | 0 | 2024-12-04 23:04 | Fadhel Haji | project | Soft crawler | 1
| 3.1 |  | Develop conceptual designs |  | 2025-01-05 09:00 | 2025-01-12 18:00 |  | 0 | 64 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2024-12-04 23:04 | Fadhel Haji | task | Soft crawler / Design Phase | 2
| 3.2 |  | Design PCB and integration for sensors and camers |  | 2025-01-06 09:00 | 2025-01-09 18:00 |  | 0 | 32 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2024-12-04 23:06 | Fadhel Haji | task | Soft crawler / Design Phase | 2
| 3.3 |  | Plan for waterproofing and environmental resilience |  | 2025-01-09 09:00 | 2025-01-10 18:00 |  | 0 | 16 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2024-12-04 23:08 | Fadhel Haji | task | Soft crawler / Design Phase | 2
| 4 | Prototyping |  |  | 2025-01-11 09:00 | 2025-01-23 18:00 |  | 0 | 104 | 0 | 0 |  |  |  |  | 0 | 0 | 2024-12-04 23:10 | Fadhel Haji | project | Soft crawler | 1
| 4.1 |  | assemble the mold pieces |  | 2025-01-11 09:00 | 2025-01-18 18:00 |  | 0 | 64 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2024-12-04 23:10 | Fadhel Haji | task | Soft crawler / Prototyping | 2
| 4.2 |  | Assemble electric wiring and components |  | 2025-01-19 09:00 | 2025-01-23 18:00 |  | 0 | 40 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2024-12-04 23:11 | Fadhel Haji | task | Soft crawler / Prototyping | 2
| 5 | Software development |  |  | 2025-01-25 09:00 | 2025-01-31 18:00 |  | 0 | 56 | 0 | 0 |  |  |  |  | 0 | 0 | 2024-12-04 23:18 | Fadhel Haji | project | Soft crawler | 1
| 5.1 |  | Develop control software for the robot's movement and camera operation |  | 2025-01-25 09:00 | 2025-01-31 18:00 |  | 0 | 56 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2024-12-04 23:18 | Fadhel Haji | task | Soft crawler / Software development | 2
| 5.2 |  | Ensure software can handle real-time data from the sensors |  | 2025-01-31 09:00 | 2025-01-31 18:00 |  | 0 | 8 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2024-12-04 23:19 | Fadhel Haji | task | Soft crawler / Software development | 2
| 6 | Testing Phase |  |  | 2025-02-02 09:00 | 2025-02-07 18:00 |  | 0 | 48 | 0 | 0 |  |  |  |  | 0 | 0 | 2024-12-04 23:13 | Fadhel Haji | project | Soft crawler | 1
| 6.1 |  | Perform initial assembly checks |  | 2025-02-02 09:00 | 2025-02-03 18:00 |  | 0 | 16 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2024-12-04 23:13 | Fadhel Haji | task | Soft crawler / Testing Phase | 2
| 6.2 |  | Gather feedback from supervisor and other team members |  | 2025-02-03 09:00 | 2025-02-05 18:00 |  | 0 | 24 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2024-12-04 23:13 | Fadhel Haji | task | Soft crawler / Testing Phase | 2
| 6.3 |  | Analyze test results and identify areas of improvement |  | 2025-02-05 09:00 | 2025-02-07 18:00 |  | 0 | 24 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2024-12-04 23:14 | Fadhel Haji | task | Soft crawler / Testing Phase | 2
| 7 | Field testing |  |  | 2025-02-08 09:00 | 2025-02-10 18:00 |  | 0 | 24 | 0 | 0 |  |  |  |  | 0 | 0 | 2024-12-04 23:22 | Fadhel Haji | project | Soft crawler | 1
| 7.1 |  | Plan field test in controlled enviroments |  | 2025-02-08 09:00 | 2025-02-10 18:00 |  | 0 | 24 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2024-12-04 23:22 | Fadhel Haji | task | Soft crawler / Field testing | 2
| 7.2 |  | Execute test in an actual pipeline |  | 2025-02-08 09:00 | 2025-02-10 18:00 |  | 0 | 24 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2024-12-04 23:23 | Fadhel Haji | task | Soft crawler / Field testing | 2
| 8 | Final adjustments |  |  | 2025-02-11 09:00 | 2025-02-14 18:00 |  | 0 | 32 | 0 | 0 |  |  |  |  | 0 | 0 | 2024-12-04 23:23 | Fadhel Haji | project | Soft crawler | 1
| 8.1 |  | Make necessary enhancements to the design based on the field collected data |  | 2025-02-11 09:00 | 2025-02-14 18:00 |  | 0 | 32 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2024-12-04 23:23 | Fadhel Haji | task | Soft crawler / Final adjustments | 2
| 9 | Documentation and reporting |  |  | 2025-02-16 09:00 | 2025-02-23 18:00 |  | 0 | 64 | 0 | 0 |  |  |  |  | 0 | 0 | 2024-12-04 23:25 | Fadhel Haji | project | Soft crawler | 1
| 9.1 |  | Document each process such as research, design and planning |  | 2025-02-16 09:00 | 2025-02-23 18:00 |  | 0 | 64 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2024-12-04 23:25 | Fadhel Haji | task | Soft crawler / Documentation and reporting | 2
| 10 | Project review |  |  | 2024-11-13 09:00 | 2025-04-23 18:00 |  | 0 | 1296 | 0 | 0 |  |  |  |  | 0 | 0 | 2024-12-04 23:26 | Fadhel Haji | project | Soft crawler | 1
| 10.1 |  | Discuss outcomes with team members |  | 2025-02-24 09:00 | 2025-02-25 18:00 |  | 0 | 16 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2024-12-04 23:26 | Fadhel Haji | task | Soft crawler / Project review | 2
| 10.2 |  | Gather feedback and discuss lessons learned |  | 2025-02-25 09:00 | 2025-02-28 18:00 |  | 0 | 32 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2024-12-04 23:28 | Fadhel Haji | task | Soft crawler / Project review | 2
| 10.3 |  | Close project |  | 2024-11-13 09:00 | 2025-04-23 18:00 |  | 0 | 1296 | 0 | 0 | Open | Medium |  |  | 0 | 0 | 2024-12-04 23:28 | Fadhel Haji | task | Soft crawler / Project review | 2
This document has been created with the help of https://ganttpro.com online service